## Tasks
Task ID | Task Name | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels | Description | Duration
altn--riMkOJR2CevtszxcgAK1lg | Requirement Gathering | Initiating | Completed | Medium |  | KHOO ZHEN XIAN | 27/10/2025 | 2025-10-06 | 13/10/2025 | false | false | 27/10/2025 | KHOO ZHEN XIAN |  |  |  |  | 7
IhDISVb2EES75jhGVhwh4cgADLs8 | Define Roles and Responsibilities | Planning | Completed | Medium |  | KHOO ZHEN XIAN | 27/10/2025 | 2025-10-13 | 15/10/2025 | false | false | 27/10/2025 | FARIZ DANISH BIN FADLI |  |  |  |  | 2
dfQ5TMtgekqLctGJcwcI-MgABgEo | Create Workflow Diagram | Initiating | Completed | Medium |  | KHOO ZHEN XIAN | 27/10/2025 | 2025-10-13 | 20/10/2025 | false | false | 27/10/2025 | KHOO ZHEN XIAN |  |  |  |  | 7
gawWXoCo80atnyRXvCyi9MgAEMzG | Define Project Concept | Initiating | Completed | Medium |  | KHOO ZHEN XIAN | 27/10/2025 | 2025-10-13 | 20/10/2025 | false | false | 27/10/2025 | KHOO ZHEN XIAN |  |  |  |  | 7
GqgX3eIfWUWB1GA61Jex68gAKcoJ | Develop Project Plan | Planning | In progress | Medium |  | KHOO ZHEN XIAN | 27/10/2025 | 2025-10-27 | 30/10/2025 | false | false | [6 empty] | 3
eoF59c62XU-R3b9lj63MncgAEiGu | Identify Dataset | Data Collection & Preparation | Not started | Medium |  | FARIZ DANISH BIN FADLI | 27/10/2025 | 2025-10-30 | 03/11/2025 | false | false | [6 empty] | 4
Y1GqwGemw0G7mOo6wb4jY8gAJFzK | Data Cleaning | Data Collection & Preparation | Not started | Medium |  | FARIZ DANISH BIN FADLI | 27/10/2025 | 2025-11-03 | 06/11/2025 | false | false | [6 empty] | 3
wEJ6Xp8at0-QPJrzvdErx8gAF8Mv | Text Preprocessing | Data Collection & Preparation | Not started | Medium |  | FARIZ DANISH BIN FADLI | 27/10/2025 | 2025-11-07 | 10/11/2025 | false | false | [6 empty] | 3
x0TPLatZzEG0TiBfHGMK58gALXEw | Feature Extraction | Model Development | Not started | Medium |  | FARIZ DANISH BIN FADLI | 27/10/2025 | 2025-11-10 | 17/11/2025 | false | false | [6 empty] | 7
ERveSpUhPE6JUzsJD4A0lsgAPsoM | Model Training | Model Development | Not started | Medium |  | FARIZ DANISH BIN FADLI | 27/10/2025 | 2025-11-17 | 01/12/2025 | false | false | [6 empty] | 14
VminW4lTykqQFbo4vkXlucgAISRY | Model Evaluation | Model Development | Not started | Medium |  | FARIZ DANISH BIN FADLI | 27/10/2025 | 2025-12-01 | 08/12/2025 | false | false | [6 empty] | 7
zif-JfnzREGqTmx2qyMbVsgAFtyp | Build Prototype Interface | System Integration | Not started | Medium |  | FARIZ DANISH BIN FADLI | 27/10/2025 | 2025-12-08 | 11/01/2026 | false | false | [6 empty] | 34
oDpxxbxJwk2c8BjbY3sGKMgACr4c | Integrate Model | System Integration | Not started | Medium |  | FARIZ DANISH BIN FADLI | 27/10/2025 | 2026-01-05 | 11/01/2026 | false | false | [6 empty] | 6
9CI91GS5ek-wo2r7LtjsF8gAMU1B | Prepare Report & Slides | Documentation & Presentation | Not started | Medium |  | FARIZ DANISH BIN FADLI | 27/10/2025 | 2026-01-10 | 19/01/2026 | false | false | [6 empty] | 9
odl7pK4-UEeSf43Cmgn8AcgANh2i | Final Presentation | Documentation & Presentation | Not started | Medium |  | FARIZ DANISH BIN FADLI | 27/10/2025 | 2026-01-10 | 19/01/2026 | false | false | [6 empty] | 9
10vTzIbM5EC9BGuetgCE9sgABfJ3 | Improve Performance | Testing & Refinement | Not started | Medium |  | FARIZ DANISH BIN FADLI | 27/10/2025 | 2026-01-12 | 19/01/2026 | false | false | [6 empty] | 7
Ecrl7_7uhUy_FBl_qCVo2MgAORy4 | Conduct Testing | Testing & Refinement | Not started | Medium |  | FARIZ DANISH BIN FADLI | 27/10/2025 | 2026-01-12 | 17/01/2026 | false | false | [6 empty] | 5
2026-12-08

## Plan name
Plan name | News Topic Classification Project
Plan ID | f1Bhg4vz_kCDx_8-44zyxsgAFQ2o
Date of export | 27/10/2025