## Tasks
Task ID | Task Name | Estimated Cost (RM) | Bucket Name | Progress | Priority | Assigned To | Created By | Created Date | Start date | Due date | Is Recurring | Late | Completed Date | Completed By | Completed Checklist Items | Checklist Items | Labels
10vTzIbM5EC9BGuetgCE9sgABfJ3 | Improve Performance | 200 | Testing & Refinement | Not started | Medium | AHMAD MIRZA SHAHMI BIN ABDUL HANIF | FARIZ DANISH BIN FADLI | 10/27/2025 | 01/12/2026 | 01/19/2026 | false | false
9CI91GS5ek-wo2r7LtjsF8gAMU1B | Prepare Report & Slides | 250 | Documentation & Presentation | Not started | Medium | AQEM ZAKWAN BIN AHMAD;FARIZ DANISH BIN FADLI;AHMAD MIRZA SHAHMI BIN ABDUL HANIF;KHOO ZHEN XIAN | FARIZ DANISH BIN FADLI | 10/27/2025 | 01/10/2026 | 01/19/2026 | false | false
ERveSpUhPE6JUzsJD4A0lsgAPsoM | Model Training | 100 | Model Development | Not started | Medium | FARIZ DANISH BIN FADLI | FARIZ DANISH BIN FADLI | 10/27/2025 | 11/17/2025 | 12/01/2025 | false | false
Ecrl7_7uhUy_FBl_qCVo2MgAORy4 | Conduct Testing | 200 | Testing & Refinement | Not started | Medium | FARIZ DANISH BIN FADLI | FARIZ DANISH BIN FADLI | 10/27/2025 | 01/12/2026 | 01/17/2026 | false | false
GqgX3eIfWUWB1GA61Jex68gAKcoJ | Develop Project Plan | 150 | Planning | Completed | Medium | AQEM ZAKWAN BIN AHMAD;FARIZ DANISH BIN FADLI;AHMAD MIRZA SHAHMI BIN ABDUL HANIF;KHOO ZHEN XIAN | KHOO ZHEN XIAN | 10/27/2025 | 10/27/2025 | 10/30/2025 | false | false | 10/27/2025 | AHMAD MIRZA SHAHMI BIN ABDUL HANIF
IhDISVb2EES75jhGVhwh4cgADLs8 | Define Roles and Responsibilities | 75 | Planning | Completed | Medium | KHOO ZHEN XIAN | KHOO ZHEN XIAN | 10/27/2025 | 10/13/2025 | 10/15/2025 | false | false | 11/05/2025 | KHOO ZHEN XIAN
VminW4lTykqQFbo4vkXlucgAISRY | Model Evaluation | 125 | Model Development | Not started | Medium | AQEM ZAKWAN BIN AHMAD | FARIZ DANISH BIN FADLI | 10/27/2025 | 12/01/2025 | 12/08/2025 | false | false
Y1GqwGemw0G7mOo6wb4jY8gAJFzK | Data Cleaning | 200 | Data Collection & Preparation | Not started | Medium | AQEM ZAKWAN BIN AHMAD | FARIZ DANISH BIN FADLI | 10/27/2025 | 11/03/2025 | 11/06/2025 | false | true
altn--riMkOJR2CevtszxcgAK1lg | Requirement Gathering | 250 | Initiating | Completed | Medium | AQEM ZAKWAN BIN AHMAD;FARIZ DANISH BIN FADLI;AHMAD MIRZA SHAHMI BIN ABDUL HANIF;KHOO ZHEN XIAN | KHOO ZHEN XIAN | 10/27/2025 | 10/06/2025 | 10/13/2025 | false | false | 11/05/2025 | KHOO ZHEN XIAN
dfQ5TMtgekqLctGJcwcI-MgABgEo | Create Workflow Diagram | 100 | Initiating | Completed | Medium | AHMAD MIRZA SHAHMI BIN ABDUL HANIF;FARIZ DANISH BIN FADLI;AQEM ZAKWAN BIN AHMAD;KHOO ZHEN XIAN | KHOO ZHEN XIAN | 10/27/2025 | 10/13/2025 | 10/20/2025 | false | false | 10/27/2025 | KHOO ZHEN XIAN
eoF59c62XU-R3b9lj63MncgAEiGu | Identify Dataset | 125 | Data Collection & Preparation | Completed | Medium | FARIZ DANISH BIN FADLI | FARIZ DANISH BIN FADLI | 10/27/2025 | 10/30/2025 | 11/03/2025 | false | false | 11/05/2025 | KHOO ZHEN XIAN
gawWXoCo80atnyRXvCyi9MgAEMzG | Define Project Concept | 200 | Initiating | Completed | Medium | AHMAD MIRZA SHAHMI BIN ABDUL HANIF;FARIZ DANISH BIN FADLI;AQEM ZAKWAN BIN AHMAD;KHOO ZHEN XIAN | KHOO ZHEN XIAN | 10/27/2025 | 10/13/2025 | 10/20/2025 | false | false | 10/27/2025 | KHOO ZHEN XIAN
oDpxxbxJwk2c8BjbY3sGKMgACr4c | Integrate Model | 250 | System Integration | Not started | Medium | AHMAD MIRZA SHAHMI BIN ABDUL HANIF | FARIZ DANISH BIN FADLI | 10/27/2025 | 01/05/2026 | 01/11/2026 | false | false
odl7pK4-UEeSf43Cmgn8AcgANh2i | Final Presentation | 100 | Documentation & Presentation | Not started | Medium | AHMAD MIRZA SHAHMI BIN ABDUL HANIF;AQEM ZAKWAN BIN AHMAD;FARIZ DANISH BIN FADLI;KHOO ZHEN XIAN | FARIZ DANISH BIN FADLI | 10/27/2025 | 01/10/2026 | 01/19/2026 | false | false
wEJ6Xp8at0-QPJrzvdErx8gAF8Mv | Text Preprocessing | 150 | Data Collection & Preparation | Not started | Medium | AHMAD MIRZA SHAHMI BIN ABDUL HANIF | FARIZ DANISH BIN FADLI | 10/27/2025 | 11/07/2025 | 11/10/2025 | false | false
x0TPLatZzEG0TiBfHGMK58gALXEw | Feature Extraction | 150 | Model Development | Not started | Medium | KHOO ZHEN XIAN | FARIZ DANISH BIN FADLI | 10/27/2025 | 11/10/2025 | 11/17/2025 | false | false
zif-JfnzREGqTmx2qyMbVsgAFtyp | Build Prototype Interface | 300 | System Integration | Not started | Medium | KHOO ZHEN XIAN | FARIZ DANISH BIN FADLI | 10/27/2025 | 12/08/2025 | 01/11/2026 | false | false

## Plan name
Plan name | News Topic Classification Project
Plan ID | f1Bhg4vz_kCDx_8-44zyxsgAFQ2o
Date of export | 11/10/2025