## Sheet1
ID | Activity Name | Duration | Pred 1 | Pred 2 | ES | EF | LS | LF | Slack | Critical?
A | Requirement Gathering | 7 |  |  | 0 | 7 | 58 | 65 | 58 | -
B | Define Project Concept | 7 | A |  | 7 | 14 | 65 | 72 | 58 | -
C | Develop Project Plan | 3 | B |  | 14 | 17 | 72 | 75 | 58 | -
D | Define Roles & Responsibilities | 2 | B |  | 14 | 16 | 73 | 75 | 59 | -
E | Create Workflow Diagram | 7 | C | D | 17 | 24 | 75 | 82 | 58 | -
F | Identify Dataset | 4 | E |  | 24 | 28 | 82 | 86 | 58 | -
G | Data Cleaning | 3 | E |  | 24 | 27 | 73 | 76 | 49 | -
H | Text Preprocessing | 3 | G |  | 27 | 30 | 76 | 79 | 49 | -
ID | Feature Extraction | 7 | H |  | 30 | 37 | 79 | 86 | 49 | -
J | Model Training | 14 | I |  | 0 | 14 | 0 | 14 | 0 | CRITICAL
K | Model Evaluation | 7 | J |  | 14 | 21 | 14 | 21 | 0 | CRITICAL
L | Improve Performance | 7 | K |  | 21 | 28 | 21 | 28 | 0 | CRITICAL
M | Conduct Testing | 5 | K |  | 21 | 26 | 23 | 28 | 2 | -
N | Integrate Model | 6 | L | M | 28 | 34 | 28 | 34 | 0 | CRITICAL
O | Build Prototype Interface | 34 | N |  | 34 | 68 | 34 | 68 | 0 | CRITICAL
P | Prepare Report & Slides | 9 | C | O | 68 | 77 | 68 | 77 | 0 | CRITICAL
Q | Final Presentation | 9 | P |  | 77 | 86 | 77 | 86 | 0 | CRITICAL
Critical Path (PDM)
Activities with zero slack:
Model Training
Model Evaluation
Improve Performance
Integrate Model
Build Prototype Interface
Prepare Report & Slides
Final Presentation
Confirmed Critical Path:
Crashing Analysis
Activity | Original Duration | Crashed Duration | Days Saved | Extra Cost
J | 14 | 13 | 1 | 150
K | 7 | 6 | 1 | 175
New Project Duration: 84 days
Total Crashing Cost: RM325