## Sheet1
Resource Identifcation
WBS ID | Task | Resource Type | Resource Name | Quantity / Hours | Description
1.1 | Define Project Concept | Human | Ahmad Mirza, Fariz, Aqem, Khoo | 8 hrs | Brainstorming and drafting project concept document.
1.2 | Requirement Gathering | Human | Fariz, Aqem, Ahmad Mirza, Khoo | 10 hrs | Gathering and documenting user and system requirements.
1.3 | Create Workflow Diagram | Human, Software | Ahmad Mirza; Draw.io | 4 hrs | Designing the system workflow diagram using diagramming tools.
2.1 | Define Roles and Responsibilities | Human | Khoo | 3 hrs | Assigning roles and defining team responsibilities.
2.2 | Develop Project Plan | Human, Software | Ahmad Mirza, Aqem, Fariz, Khoo; MS Project, Google Sheets | 6 hrs | Developing timeline, milestones, and deliverables in project plan.
3.1 | Identify Dataset | Human, Software | Fariz; Kaggle | 5 hrs | Searching, downloading, and storing suitable datasets.
3.2 | Data Cleaning | Human, Software | Aqem; Python (Pandas), Jupyter Notebook | 8 hrs | Cleaning and organizing raw data for analysis.
3.3 | Text Preprocessing | Human, Software | Ahmad Mirza; Python (NLTK, Regex) | 6 hrs | Removing noise, tokenizing, and preparing text data.
4.1 | Feature Extraction | Human, Software | Khoo; Python (TF-IDF, Scikit-learn) | 6 hrs | Extracting key features from text data for model training.
4.2 | Model Training | Human, Software, Hardware | Fariz; Python (TensorFlow), Scikit-learn, Google Colab | 10 hrs | Training machine learning model using available hardware.
4.3 | Model Evaluation | Human, Software | Aqem; Python (Matplotlib), Jupyter Notebook | 5 hrs | Evaluating model performance using metrics and charts.
5.1 | Build Prototype Interface | Human, Software | Khoo; Figma, Flutter | 12 hrs | Designing and developing the prototype user interface.
5.2 | Integrate Model | Human, Software | Ahmad Mirza; Flask API, Flutter | 10 hrs | Integrating trained model into the mobile application.
6.1 | Conduct Testing | Human, Software | Fariz; PyTest, Postman | 8 hrs | Conducting functional and integration testing.
6.2 | Improve Performance | Human, Software, Hardware | Ahmad Mirza; Python Optimization, GPU, Google Colab | 8 hrs | Enhancing model and system performance.
7.1 | Prepare Report & Slides | Human, Software | Khoo, Ahmad Mirza, Aqem, Fariz; MS Word, PowerPoint | 10 hrs | Preparing final project report and presentation slides.
7.2 | Final Presentation | Human, Equipment | Team; Laptop, Projector | 4 hrs | Presenting the final system to evaluators.
Task Cost Estimation
WBS Task |  | Hours | Resource Type | Rate (RM/hr) | Total Cost (RM)
Define Project Concept |  | 8 | Human | 25 | 200
Requirement Gathering |  | 10 | Human | 25 | 250
Create Workflow Diagram |  | 4 | Human | 25 | 100
Define Roles & Responsibilities |  | 3 | Human | 25 | 75
Develop Project Plan |  | 6 | Human | 25 | 150
Identify Dataset |  | 5 | Human | 25 | 125
Data Cleaning |  | 8 | Human | 25 | 200
Text Preprocessing |  | 6 | Human | 25 | 150
Feature Extraction |  | 6 | Human | 25 | 150
Model Training (GPU) |  | 10 | Hardware (GPU) | 10 | 100
Model Evaluation |  | 5 | Human | 25 | 125
Build Prototype Interface |  | 12 | Human | 25 | 300
Integrate Model |  | 10 | Human | 25 | 250
Conduct Testing |  | 8 | Human | 25 | 200
Improve Performance |  | 8 | Human | 25 | 200
Prepare Report & Slides |  | 10 | Human | 25 | 250
Final Presentation |  | 4 | Human | 25 | 100
Budget Summary
Cost Category |  | Example Items / Tasks |  | Subtotal (RM)
Human Resources |  | Project concept, requirement gathering, workflow design, testing, documentation, etc. |  | 2825
Hardware / Cloud |  | GPU instance for model training |  | 100
Software / Licenses |  | Draw.io, PowerPoint (free/open-source assumed) |  | 0
Communication |  | Online meetings, file sharing (Teams, GitHub, etc.) |  | 0
Total Estimated Budget |  |  |  | 2925